## Info
🤔 Why keep a logbook?
Keep track of your competences
Gain insights for reflection
Build a knowledge base
Your learning process, your responsibility
😅 How can you contribute?
💼 Project Management
👔 Professional Skills
🔍 Analysis
📏 Design
🛠️ Realize
Description of the competences

## Activity
When? (use [CTRL] + [;] to enter date) | In short, what did you do? | Duration (hours) | Provide the details (include steps taken, actions, links when possible) | Total Worktime
2023-11-27 | Create basic template with config support | 1:00 | I made the first bit of code so we could start the project. One central config file would be smart so we decided to add it. | 46:30
2023-11-27 | Create basic sprite system | 2:00 | I made the beginning of the sprite system. The sprites of the player can now be changed with an index.
2023-11-27 | Animate sprites so we know shifting sprites works | 3:00 | I dedcided to animate the sprites so I knew sprite animations where possible. This took some time but I managed to pull it off
2023-11-27 | Replace animations with keydown events so sprite is based on movement | 2:00 | The player is no longer animated, the sprites are now switched if we press W/A/S/D.
2023-11-27 | Add respawn system (move player based on pixel color) | 2:00 | The game now detects if there is a certain 'respawn color' right under the player. If there is, it will respawn the player and show text
2023-11-27 | Add sound mixer so sound can be played | 2:00 | I wanted sound if the player was respawning so I added a simple sound mixer.
2023-11-28 | Create event manager | 2:00 | Today I wanted to 'simplify' player events, such as respawning. It took some time but the event manager worked.
2023-11-28 | Improve respawn system | 2:00 | With the new event manager I needed to change the way the respawn system worked. This works like a charm.
2023-11-28 | polish the code | 2:00 | I decided to clean up our project. This means remove unnesserary code from the code I have written and move files into folders instead of having everything in our root.
2023-11-28 | improve music mixer by using separate audio channels | 2:00 | With the new respawn system there came an issue regarding the music mixer, sound could be stacked. This is why I introduced sound channels and the music mixer's very own class.
2023-11-28 | Managed and improved planning | 2:00 | Since the beginning of today we had our planning on Github. At the end of the day we were fully utilizing "Issues" to see what we did, what we needed to, and what we are currently doing.
2023-11-29 | Tried to implement camera and map system | 3:00 | I tried to implement the camera and map system. But I couldn't concentrate well. Right after I needed to go to school for a meeting.
2023-11-29 | Implemented player boost on left shift | 1:00 | When I came home I quickly introduced player boosts. I could concentrate again! :D
2023-11-29 | Removed bug; riding out of the defined window size is no longer possible. | 2:00 | With my new found concentration I squashed a bug. This way, regardless of if we have a camera or not we would never crash because of an out of bounds error.
2023-11-29 | You can trigger the menu by pressing escape while in game | 0:30 | Menu now opens if you press escape. Menu buttons don’t entirly work yet in this state (do work if the menu is triggered before playing)
2023-11-30 | Added new player sprite (Wario) | 1:00 | I just added a new sprite. Photoshop was required in order to get the right format. This took longer then expected but it works.
2023-11-30 | Added new player respawn sound (Wario) | 0:30 | Quickly changed the respawn system so it uses a new respawn sound. This sound is acurate to the player sprite.
2023-11-30 | Added game icon | 0:30 | I added a game icon, this makes the game a tiny bit prettier.
2023-11-30 | Adjust player speed if moving diagonally | 2:00 | With some-what of a gradual movement and a player boost the player obviously can't speed though turns. If they can they would, possibly, die to quickly
2023-11-30 | Fix gradual player movement | 1:00 | The gradual movement had a small 'stutter' bug in it. This issue is now solved by introducing integer rounding and always setting the player speed to 0 if the player doesn't press any keys. - The gradual movement is only really noticable when you just start boosting.
2023-11-30 | Finally worked on my logbook. | 1:00 | Filled in my logbook by looking at the Github entries. I had saved the times I started and ended (hours worked) so I can fill it in accurately .
2023-11-30 | Added track music | 0:30 | Rainbow Road time! - Music stops when the player is either gameover or, theoretially, finishes!
2023-11-30 | Bug fixing with Jonathan | 2:00 | Finding and squashing bugs with Jonathan. Such as but not limited to 1) Audio not looping and 2) flying off the track without the respawn system triggering
2023-12-01 | Improved code documentation + moved some code | 2:00 | Added documentation, moved code, and tested the game multiple times to make sure everything still worked. Also added some items to the kanban board we have on Github.
2023-12-01 | Updated my logbook | 0:30 | Added some items and images
2023-12-01 | Added finish line | 4:00 | Adding the finish line took some time as I needed to chane both the code and the map. I also added and fixed each sound for each finished lap and for when you actually finish.
2023-12-01 | Researched and played with AI so we can make a player 2 | 3:00 | Did research on AI with pygame and tested example code.

## Drop down items (hidden)
Drop down items
💼 Project Management
👔 Professional Skills
🔍 Analysis
📏 Design
🛠️ Realize
🦥
⭐
⭐⭐
⭐⭐⭐